**Project: Woodson Park Academy & YMCA-ELC**

**Week Ending: October 11th, 2019**

**THIS WEEK:**

* Foundations wall pours
* Pour north side footer
* Storm line install continued
* Waterproofing of foundation wall continues
* Pour upper level piers
* Set pole for Temp power

**![A close up of a fence

Description automatically generated]() ![A picture containing outdoor, sky, tree, building

Description automatically generated]()**

**![A picture containing sky, outdoor, ground

Description automatically generated]() ![A truck driving down a dirt road

Description automatically generated]()**

**NEXT WEEK – October 14 thru October 18:**

* Foundation wall
* Storm line install
* Cutting of NE parking lot grade
* Waterproofing
* Upper level peirs

**PAYMENT STATUS:**

* Gmp#1 $3,703,488.00
  + Paid to date amount $646,892.85
* GMP#2 $28,686,295.00
  + Paid to date amount $0.00

**SCHEDULED DATE OF SUBSTANTIAL COMPLETION**

* WPA – September 28, 2020
* YMCA-ELC - September 16, 2020

**PREPARED BY:**

* **Matt Dauber, Carroll Daniel Construction Co.**