**Project: Woodson Park Academy & YMCA-ELC**

**Week Ending: October 18th, 2019**

**THIS WEEK:**

* Foundations wall pours
* Storm Line B completed
* Upper Detention pond completed
* Started lower level MEP
* Waterproofing at retaining wall
* Retaining wall backfill started

**A picture containing ground, sky, outdoor, fence

Description automatically generated A picture containing indoor, wall, ground

Description automatically generated**

**A picture containing ground, building, indoor, sitting

Description automatically generated A picture containing indoor, wall, table, person

Description automatically generated**

**NEXT WEEK – October 21 thru October 25:**

* Complete foundation wall
* Complete lower level piers
* Continue underslab MEP
* Start slab prep at kitchen area

**PAYMENT STATUS:**

* Gmp#1 $3,703,488.00
  + Paid to date amount $646,892.85
* GMP#2 $28,686,295.00
  + Paid to date amount $0.00

**SCHEDULED DATE OF SUBSTANTIAL COMPLETION**

* WPA – September 28, 2020
* YMCA-ELC - September 16, 2020

**PREPARED BY:**

* **Matt Dauber, Carroll Daniel Construction Co.**