**Project: Woodson Park Academy & YMCA-ELC**

**Week Ending: November 1st, 2019**

**THIS WEEK:**

* Lower level MEP’s continued
* Waterproofing at retaining wall
* Retaining wall backfill started

**A picture containing ground, outdoor, sky, fence

Description automatically generated A picture containing ground, outdoor, building, sky

Description automatically generated**

**A picture containing ground, person, building, outdoor

Description automatically generated A picture containing ground, outdoor, sky, building

Description automatically generated**

**NEXT WEEK – November 4th thru November 8th:**

* Continue underslab MEP
* Start slab prep at kitchen area
* Pour slab at kitchen area.

**PAYMENT STATUS:**

* Gmp#1 $3,703,488.00
  + Paid to date amount $1,469,778.75
* GMP#2 $28,686,295.00
  + Paid to date amount $1,124,342.82

**SCHEDULED DATE OF SUBSTANTIAL COMPLETION**

* WPA – September 28, 2020
* YMCA-ELC - September 14, 2020

**PREPARED BY:**

* **Matt Dauber, Carroll Daniel Construction Co.**