**Project: Woodson Park Academy & YMCA-ELC**

**Week Ending: November 29, 2019**

**THIS WEEK:**

* Masonry continues
* Retaining wall backfill
* Cut Parking lot grades
* UG MEPS continues
* Steel Sub mobilization

** **

 ** **

**NEXT WEEK – December 2nd thru December 6th:**

* Continue underslab MEP
* Masonry continues
* Start Structural Steel

**PAYMENT STATUS:**

* Gmp#1 $3,703,488.00
	+ Paid to date amount $1,469,778.75
* GMP#2 $28,686,295.00
	+ Paid to date amount $1,124,342.82

**SCHEDULED DATE OF SUBSTANTIAL COMPLETION**

* WPA – September 28, 2020
* YMCA-ELC - September 14, 2020

**PREPARED BY:**

* **Matt Dauber, Carroll Daniel Construction Co.**