**Project: Woodson Park Academy & YMCA-ELC**

**Week Ending: August 2nd, 2019**

**THIS WEEK:**

* Building demo has resumed
* Tub grinder grinding stumps and tree tops
* Tree haul off

A herd of animals walking across a dirt field

Description automatically generated A group of people on a dirt road

Description automatically generated

**A truck driving down a dirt road

Description automatically generated**

**NEXT WEEK – August 5 thru August 9:**

* Demo Continues
* Tire crew to remove tires
* Grubbing and tree haul off to continue

**PAYMENT STATUS:**

* Gmp#1 $3,703,488.00
  + Paid to date amount $0.00
* GMP#2 $28,686,295.00
  + Paid to date amount $0.00

**SCHEDULED DATE OF SUBSTANTIAL COMPLETION**

* WPA – September 17, 2020
* YMCA-ELC - September 14, 2020

**PREPARED BY:**

* **Matt Dauber, Carroll Daniel Construction Co.**