**Project: Woodson Park Academy & YMCA-ELC**

**Week Ending: August 23rd, 2019**

**THIS WEEK:**

* Waiting on French drain design / feedback due to water
* Continued building pad
* Continued site concrete haul off
* Hauled in fill material

 

** **

**NEXT WEEK – August 26 thru August 30:**

* Grading continues
* French drain design
* Concrete haul off
* Fill haul in

**PAYMENT STATUS:**

* Gmp#1 $3,703,488.00
	+ Paid to date amount $0.00
* GMP#2 $28,686,295.00
	+ Paid to date amount $0.00

**SCHEDULED DATE OF SUBSTANTIAL COMPLETION**

* WPA – September 28, 2020
* YMCA-ELC - September 16, 2020

**PREPARED BY:**

* **Matt Dauber, Carroll Daniel Construction Co.**