**Project: Woodson Park Academy & YMCA-ELC**

**Week Ending: September 6th, 2019**

**THIS WEEK:**

* Aggregate pier install
* Grading continued
* Storm line “A” install
* Finished French drain

**A group of people in a dirt field

Description automatically generated A large empty field

Description automatically generated**

**A train traveling down a dirt track

Description automatically generated A picture containing outdoor, ground, grass

Description automatically generated**

**NEXT WEEK – September 9 thru September 13:**

* Groundbreaking
* Aggregate pier to be completed on LL
* Storm line install continued
* Foundation wall rebar to be delivered

**PAYMENT STATUS:**

* Gmp#1 $3,703,488.00
  + Paid to date amount $646,892.85
* GMP#2 $28,686,295.00
  + Paid to date amount $0.00

**SCHEDULED DATE OF SUBSTANTIAL COMPLETION**

* WPA – September 28, 2020
* YMCA-ELC - September 16, 2020

**PREPARED BY:**

* **Matt Dauber, Carroll Daniel Construction Co.**